## Action List
CARDER MANAGEMENT SYSTEM — ACTION LIST
Internal review actions captured from the meeting held on 31 August 2026
Participants: Kumara Sir, Nisansala, Chanika, Janani, Sahas ¦ Open actions: 28
ACTION TRACKER
Action ID | Workstream | Action Item | Requirement / Acceptance Criteria | Owner | Priority | Status | Due Date | Dependency / Notes
A01 | Login & Roles | Define user roles | Configure three roles: Admin, Super User, and User. | TBD | TBD | Done | TBD | None
A02 | Login & Roles | Grant Admin full access | Admin users can access all system data and functionalities. | TBD | TBD | Done | TBD | A01
A03 | Login & Roles | Add privilege administration | Admin can grant and manage access and privileges for Super Users and Users. | TBD | TBD | Done | TBD | A01
A04 | Dashboard | Add country filter | Dashboard supports country-wise filtering. | TBD | TBD | Pending | TBD | None
A05 | Dashboard | Add factory filter | Dashboard supports factory-wise filtering. | TBD | TBD | Pending | TBD | None
A06 | Dashboard | Apply dashboard access rules | Admins see all countries and factories; other users see only data allowed by Admin privileges. | TBD | TBD | Pending | TBD | A03, A04, A05
A07 | Dashboard | Build required dashboard charts | Include Carder Fulfilment, Carder Trend, Requirement and Resign, LTO – Auto, LTO – Analysis by Service, LTO Analysis – Service Reason, and Absent Reason. | TBD | TBD | Pending | TBD | Dashboard data availability
A08 | Week Definition | Set week start to Tuesday | The system week begins on Tuesday. | TBD | TBD | Done | TBD | None
A09 | Week Definition | Apply Tuesday-based cycle | All weekly calculations, reports, and weekly views follow the Tuesday-based week cycle. | TBD | TBD | Done | TBD | A08
A10 | TMO / Recruitment | Auto-post transfers | Automatically add Transfer to Production Line values to New Recruitment MO / Rejoined MO / TMO Released from Training Center. | TBD | TBD | Done | TBD | Source allocation data
A11 | TMO / Recruitment | Add two new sections | Develop two additional sections in the system. | TBD | TBD | Pending input | TBD | A12
A12 | TMO / Recruitment | Confirm detailed requirements | Obtain detailed requirements for the two new sections from Kumar Sir. | Kumar Sir | TBD | Pending input | TBD | Kumar Sir input
A13 | Next Date | Auto-fill Next Date | Automatically populate Next Date from the relevant allocation and planning information. | TBD | TBD | Partial | TBD | Allocation/planning data
A14 | Next Date | Include allocation inputs | Next Date logic considers Allocated Actual MO and Allocated Actual TMO. | TBD | TBD | Open | TBD | A13
A15 | Planned MO & TMO | Use default planned values | Planned MO and Planned TMO initially use their corresponding default values. | TBD | TBD | Done | TBD | Default-value rules
A16 | Planned MO & TMO | Allow planned value changes | Users can modify Planned MO and Planned TMO when required. | TBD | TBD | Done | TBD | A15
A17 | Planned MO & TMO | Create update/edit screen | Provide an Update/Edit screen for changing Planned MO and Planned TMO. | TBD | TBD | Done | TBD | A16
A18 | Weekly View | Show planned staffing | Add Planned MO and Planned TMO to the Weekly View. | TBD | TBD | Open | TBD | A09, A15
A19 | Resign | Create resign entry form | Add a dedicated form to track and maintain employee resignation details. | TBD | TBD | Open | TBD | None
A20 | Resign | Add resign form fields | Include EPF No. and Name as manual entry; Designation, Department, and Section as dropdowns; Joining and Resign dates as date pickers; Service Period as auto-calculated; Reason for Resign as manual entry. | TBD | TBD | Open | TBD | A19
A21 | Resign | Calculate service period | Automatically calculate Service Period as Date of Resign minus Date of Joining. | TBD | TBD | Open | TBD | A20
A22 | Resign | Assign HR service category | Automatically assign the HR Service Category from the calculated service period using categories defined by HR. | TBD | TBD | Open | TBD | A21, HR category definitions
A23 | Resign | Support resign categories | Classify resignation records as Line or Training Center. | TBD | TBD | Open | TBD | A19
A24 | Resign | Add combined and separate views | Provide All, Line, and Training Center views: All combines both categories; the other tabs filter to one category. | TBD | TBD | Open | TBD | A23
A25 | Master Data | Make Reason and Category dropdowns | Provide Reason and Category fields as dropdown controls. | TBD | TBD | Open | TBD | A26
A26 | Master Data | Load dropdown master values | Populate dropdowns from the corresponding Master Data. | TBD | TBD | Open | TBD | A27
A27 | Master Data | Create separate masters | Develop separate Reason Master and Category Master datasets. | TBD | TBD | Open | TBD | None
A28 | Master Data | Enable master maintenance | Authorized users can add, update, and maintain Reason and Category values in Master Data. | TBD | TBD | Open | TBD | A03, A27